## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | Augmentation | Augmentation of JUGINDA (Zone - I) Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER |  | ORD/000377/2023-2024 | 2772/MURD | 01/09/2023 | 28/02/2024 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 600.58 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 1210/MURD/22 | 02/05/2023 | 02/05/2023 | Resource Division | 133.91 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JUGINDA ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001431/2023-2024 | 4311/MEDB | 29/12/2023 | 29/03/2024 | M/S DILIP MITRA | 23.67 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | Augmentation | JUGINDA PH-IV |  |  | BILL/01526/2023-2024 | 408/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.24 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 100
Total | [13 empty] | 857.93 | 0 | 0