## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 09/06/2022 | ALLIANCE INDIA | 25.34 | 4.25 | 16.77 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 1210/MURD/31 | 02/05/2023 | 02/05/2023 | Resource Division | 64.61 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V ,Zone-II under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000693/2023-2024 | 3865/MEDB | 07/11/2023 | 07/02/2024 | WEST BENGAL ENGINEERING CO. | 52.01 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | NEW SERVICE CONNECTION AT ARJUNPUR PWSS Z2 PH1 ID 304391006 |  |  | BILL/01142/2024-2025 |  | 27/11/2024 | 27/11/2024 | WBSEDCL | 4.49 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION,Junior Engineer 3 | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 10/10/2025 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 0 | 35
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 4.46 | 4.66 | 100
Total | [13 empty] | 2283.05 | 8.7 | 0.38