## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1043/MURD/7 | 17/04/2023 | 17/04/2023 | Resource Division | 84.58 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 1936/MURD | 18/07/2023 | 18/07/2023 | Resource Division | 84.58 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under MAHALANDI ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000287/2023-2024 | 583/MEDB | 31/01/2024 | 01/01/2025 | CONCORD ENGINEERING | 48.03 | 0 | 0 | 40
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Construction of Boundary Wall & Pump House with sanitary & plumbing work (H.W & 4th T/W Site) of Mahalandi (Zone-I) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000084/2024-2025 | 2088/MURD | 23/07/2024 | 21/09/2024 | AHAMMED ENTERPRISE | 21.22 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | CONSTRUCTION OF ROAD FROM GOKARNA TO ASOLAMPUR, PACKAGE NO- WB-13 -365, LENG- 10.215 KM , BLOCK KANDI, IN THE DIST MUSHIDABAD |  |  | BILL/01077/2024-2025 | 403-MSD/2024-25 | 23/09/2024 | 23/09/2024 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 5.19 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | AT MAHALANDI PH 3 ID 304239410 |  |  | BILL/01473/2023-2024 | 371/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | NEW SER VICE CONNECTION AT MAHALANDI PH 3 ID 304239410 |  |  | BILL/01491/2023-2024 |  | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Laying of Distribution System (Part-A), Construction of Over Head Reservoir (400 Cum), Pump House (3rd Site), Boundary wall (3rd Site), Repairing of Pump House & Boundary wall (H.W & 2nd Site), Repairing of Over Head Reservoir (250 Cum) and accommodate FHTC work at Mahalandi Village (Village Code-315231) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000471/2023-2024 | 3014/MURD | 26/09/2023 | 01/01/2026 | PREKSHITA CONSTRUCTION | 248.32 | 12.19 | 4.91 | 10
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Laying of Distribution System (Part-B) and FHTC work at Mahalandi Village (Village Code-315231) & Durlabhpur Village (Village Code-315218) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme in Kandi Block under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000481/2023-2024 | 3052/MURD | 29/09/2023 | 22/08/2025 | PRIYANKA CONSTRUCTION | 286.61 | 44.8 | 15.63 | 20
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | Augmentation | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 01/10/2025 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 0 | 40
Total | [13 empty] | 861.15 | 56.99 | 6.62