## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Inter connection with Tubewell and rising main etc. at Head work sites of Katakopra Water Supply scheme (Katakopra Z-I & Z-II both) and allied works under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | ASSISTANT ENGINEER | Junior Engineer | ORD/001237/2021-2022 | 43/ISD | 28/01/2022 | 29/03/2022 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 4.33 | 4.25 | 98.04 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 1167/MURD/35 | 28/04/2023 | 28/04/2023 | Resource Division | 198.12 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 1167/MURD/33 | 28/04/2023 | 28/04/2023 | Resource Division | 22 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3 | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 05/04/2024 | NADIA TUBEWELLS | 11.78 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | NEW CONNECTION AT KATAKOBRA Z-I PH-II |  |  | BILL/01099/2024-2025 |  | 13/11/2024 | 13/11/2024 | WBSEDCL | 5.81 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | NEW CONNECTION AT KATAKOBRA Z-I PH-I |  |  | BILL/01098/2024-2025 |  | 13/11/2024 | 13/11/2024 | WBSEDCL | 6.63 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-I under Katakobra ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000649/2023-2024 | 3666/MEDB | 03/11/2023 | 30/08/2025 | HARA PROSAD DAS | 22.58 | 0 | 0 | 15
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Augmentation KATAKOPRA (Zone -I) under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 8 | ORD/000474/2023-2024 | 3031/MURD | 27/09/2023 | 19/05/2025 | M/S HANNAN KHAN CONSTRUCTION | 300.03 | 44.39 | 14.79 | 15
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Laying Distribution System for Augmentation of Katakopra Zone -I & II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkol Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 8 | ORD/000172/2024-2025 | 2994/MURD | 13/11/2024 | 06/02/2026 | M/S. BIMALENDU BOSE | 389.64 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000121/2023-2024 | 1762/MURD | 06/07/2023 | 27/07/2023 | R.K. DRILLING SERVICES | 35.37 | 21.67 | 61.28 | 66
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | Augmentation | Augmentation of KATAKOPRA (Zone-I) PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 8 | ORD/000479/2023-2024 | 3050/MURD | 29/09/2023 | 01/01/2026 | M/S. BIMALENDU BOSE | 466.19 | 207 | 44.4 | 90
Total | [13 empty] | 1462.47 | 277.31 | 18.96