## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part C) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000573/2023-2024 | 3297/MURD | 20/10/2023 | 17/04/2024 | M H SUPPLIERS | 305.91 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-II |  |  | BILL/01243/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 10.75 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-I |  |  | BILL/01242/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 7.82 | 0 | 0 | 0
4 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-III |  |  | BILL/01244/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 7.42 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate Laying Distribution System & Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000480/2023-2024 | 3051/MURD | 29/09/2023 | 18/01/2025 | SOFIQUL ISLAM | 293.57 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 17/06/2025 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 13.19 | 5.21 | 100
Total | [13 empty] | 961.23 | 13.19 | 1.37