## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 13.19 | 5.21 | 100
2 | MURSHIDABAD | Suti-II | Central Drilling | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate Laying Distribution System & Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000480/2023-2024 | 3051/MURD | 29/09/2023 | 18/01/2025 | SOFIQUL ISLAM | 293.57 | 0 | 0 | 0
4 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part C) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000573/2023-2024 | 3297/MURD | 20/10/2023 | 17/04/2024 | M H SUPPLIERS | 305.91 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2 nos, Construction of Boundary Wall of 220 m, Construction 1000 Cum OHR with sub soil investigation Jal Jeevan Mission of Suti-II Block, Murshidabad. . (Part-B) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000578/2023-2024 | 3314/MURD | 22/10/2023 | 09/05/2026 | M/S. A.T.D. PROJECTS | 364.02 | 0 | 0 | 15
6 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-II |  |  | BILL/01243/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 10.75 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-III |  |  | BILL/01254/2024-2025 | 327/WBSEDCL-JJM | 17/12/2024 | 17/12/2024 | WBSEDCL | 7.42 | 0 | 0 | 0
8 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-I |  |  | BILL/01256/2024-2025 | 329/WBSEDCL-JJM | 17/12/2024 | 17/12/2024 | WBSEDCL | 7.82 | 0 | 0 | 0
9 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-I |  |  | BILL/01242/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 7.82 | 0 | 0 | 0
10 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-II |  |  | BILL/01255/2024-2025 | 328/WBSEDCL-JJM | 17/12/2024 | 17/12/2024 | WBSEDCL | 10.75 | 0 | 0 | 0
11 | MURSHIDABAD | Suti-II | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-III |  |  | BILL/01244/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 7.42 | 0 | 0 | 0
12 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 17/06/2025 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
13 | MURSHIDABAD | Suti-II | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 5 | ORD/000492/2024-2025 | 485/MURD | 25/02/2025 | 31/10/2025 | IMAGIN | 55.71 | 0 | 0 | 100
Total | [13 empty] | 22746.71 | 13.19 | 0.06