## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Repairing & rectification of Centrifugal pumping machinery sets including other allied works at Beldanga Intake under MEDB, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000880/2023-2024 | 3388/MEDB | 09/11/2023 | 09/02/2024 | CONCORD ENGINEERING | 13.92 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk ) at Intake and WTP under Augmentation of Beldanga Surface Water Based W/S Scheme in the Dist. of Murshidabad. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000143/2024-2025 | 1495/MEDB | 26/06/2024 | 26/12/2024 | MAHADEV ENTERPRISE | 320.85 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | MSD/1735 | 11/06/2024 | 11/06/2024 | Resource Division | 6.55 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Feasibility study to select a suitable location for proposed intake jetty for drawal of 23.00 MLD raw water from River Bhagirathi at Kumarpur, Beldanga-I Block. For surface water supply Scheme under Murshidabad Division in Murshidabad District. |  |  | BILL/01075/2024-2025 | 380-MSD/2024-25 | 18/09/2024 | 18/09/2024 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 60.66 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Construction of 11 Nos. different Capacity OHR including Soil test (100,200,300,400,500,600,700,750,1000 Cum), Boundary Wall, 11 Nos Operator Shed cum chlorine room with sanitary and water supply arrangement, Laying of clear water Rising Main , Laying Distribution System, Service Road , Land Development and FHTC, Bypass arrangement of OHR for Surface Water Based Water Supply Scheme in the Uncovered areas of Beldanga-I Block, under MurshidabadDivision P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000611/2023-2024 | 3376/MURD | 31/10/2023 | 01/01/2026 | M/S R B CONSTRUCTION | 7132.23 | 207.97 | 2.92 | 10
6 | MURSHIDABAD |  | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Construction of 22.1 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Substation Building ,Electro- Mechanical Works , Staff quarter & other components and SCADA on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 1(One) year for Surface Water Based piped W/S scheme in the uncovered areas of arsenic affected Beldanga-I Block in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000030/2024-2025 | 1883/MURD | 28/06/2024 | 28/09/2026 | GBC INFRASTRUCTURE PRIVATE LIMITED | 4480 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | Augmentation | Supply delivery and installation of spares of High Lift Pumping Machineries at Beldanga WTP under MEDB, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000002/2025-2026 | 958/MEDB | 23/04/2025 | 23/05/2025 | HARA PROSAD DAS | 8.24 | 0 | 0 | 0
Total | [13 empty] | 12022.44 | 207.97 | 1.73