## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Farakka | Berhampore Mechanical | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) | SM/18916 | New | Providing Electrical Equipment for 11/0.433 KV Sub-station at Water Treatment Plant under surface based water supply scheme for Bewa and its adjoining mouzas, Block - Farraka, District - Murshidabad. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001408/2023-2024 | 107/MEDB | 17/01/2024 | 17/07/2024 | CONCORD ENGINEERING | 252.48 | 0 | 0 | 0
2 | MURSHIDABAD | Farakka | Murshidabad Division | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) | SM/18916 | New | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Pre Settling Tank ,Construction of 7.765 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Indoor Type Substation Building ,Electro Mechanical Works , Staff quarter & other components, Clear Water Pumping Main, Construction of 5 (Five) Nos OHRs and Distribution system for 5 nos distribution zones with DI/HDPE/UPVC pipes, House Hold Connections , on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 5 years for Surface Water Based BEWA piped W/S scheme in Farakka Block in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000714/2023-2024 | 3836/MURD | 14/12/2023 | 13/12/2024 | CONCORD-SRG-(JV) | 8070 | 0 | 0 | 5
Total | [13 empty] | 8322.48 | 0 | 0