## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. | SM/18982 | Augmentation | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 01/12/2022 | MERCHANDISE-INDIA | 14.45 | 2.39 | 16.54 | 90
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. | SM/18982 | Augmentation | Laying Distribution system, Rising Main Connection, FHTC(834 Nos) Construction of Boundary Wall , Pump House,Sinking of 300 x 200 mm dia Rig Bore Tubewell of Sikarpur PWSS in Farakka Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000744/2023-2024 | 60/MURD | 08/01/2024 | 01/01/2026 | S.S. ENTERPRISE | 98.78 | 0 | 0 | 30
Total | [13 empty] | 113.23 | 2.39 | 2.11