## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | Augmentation | Laying Distribution System, Rising Main, , Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of BEWA Zone-II Water at Supply Scheme in FARAKKA Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3,Junior Engineer I | ORD/000603/2023-2024 | 3357/MURD | 30/10/2023 | 27/07/2026 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 120.09 | 62.54 | 52.07 | 40
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BEWA -II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000701/2023-2024 | 3769/MURD | 08/12/2023 | 31/05/2025 | HARUN ALL RASHID & BROTHERS | 35.3 | 17.77 | 50.34 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | Augmentation | Balance Work of Road restoration damaged during laying of pipeline of Bewa Zone-II Piped Water Supply Scheme, Farakka Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000849/2023-2024 | 824/MURD | 15/03/2024 | 29/11/2025 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 11.51 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 17/06/2025 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
Total | [13 empty] | 259.23 | 80.31 | 30.98