## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of One Year under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/10/2020 to 14/10/2021) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000103/2020-2021 | 2625/MURD | 08/10/2020 | 08/10/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.54 | 4.54 | 100 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of One Year under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/10/2021 to 14/04/2022) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/001247/2021-2022 | 3361/MURD | 11/10/2021 | 11/04/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 2.41 | 94.18 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophoto meter System for a Period of 06(Six) Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/04/2022 to 14/09/2022) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000162/2022-2023 | 925/MURD | 11/04/2022 | 11/10/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 0 | 0 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Arrear salary and arrear festival bonus for Chemist, Bacteriologist, Lab- Assistant and Sampling- Assistant of NABL Accredited/Recognized District and Sub-District Water testing Laboratories for January and February 2023 under Murshidabad Division, PHE Dte.(The details of personnel are attached as annexure -B) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000681/2023-2024 | 3714/MURD | 05/12/2023 | 20/12/2023 | S. DUTTA | 4.14 | 4.14 | 100 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Engagement of 02(Two) nos. Chemist (01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) , 02(Two)nos.Bacteriologist(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) and 02(Two)nos. Lab Assitant(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 01(One) year. i.e. period form 01/03/2023 to 28/02/2024 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000772/2022-2023 | 451/MURD | 17/02/2023 | 17/02/2024 | BISWAS ENGINEERING & WATER TESTING. | 16.5 | 9.1 | 55.17 | 67
6 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Engagement of 07(Seven) nos. Chemist (01 no. District Laboratory and 06nos. Sub-District Laboratory) , 06(Six)nos.Bacteriologist(01 no. District Laboratory and 05nos. Sub-District Laboratory), 11(Eleven)nos. Lab Assitant(01 no. District Laboratory and 10nos. Sub-District Laboratory) and 10(Ten)nos. Sampling Assistant(01 no. District Laboratory and 09nos. Sub-District Laboratory) in each of 11(Eleven) nos. District & Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. for 01(One) year. (i.e. period form 01/03/2023 to 28/02/2024) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000773/2022-2023 | 455/MURD | 17/02/2023 | 17/02/2024 | CLIFFORD FACILITY SERVICES PVT. LTD. | 82.31 | 63.65 | 77.33 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of Six Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/09/2023 to 14/03/2024) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000743/2023-2024 | 2916/MURD | 14/09/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 2.56 | 100 | 100
8 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/06/2023 to 31/08/2023. |  |  | BILL/00657/2023-2024 | 421-MSD/2023-24 | 07/12/2023 | 07/12/2023 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 1.7 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Bonus of Lab personnel for the period from 2023-24. |  |  | BILL/00720/2023-2024 |  | 04/10/2023 | 04/10/2023 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.16 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for festival Bonus of Lab Personnel for the period 2022-23 |  |  | BILL/00780/2023-2024 |  | 10/10/2023 | 10/10/2023 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.16 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | REIMBURSEMENT OF 2ND INSTALLMENT OF LAB 2023 |  |  | BILL/00927/2023-2024 | 419-MSD/2023-24 | 07/12/2023 | 07/12/2023 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.4 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Festival Bonus |  |  | BILL/00746/2023-2024 |  | 06/10/2023 | 06/10/2023 | R.N CLUB LAB | 0.16 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of September 2023. |  |  | BILL/00745/2023-2024 | 418-MSD/2023-24 | 07/12/2023 | 07/12/2023 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/10/2023 to 30/11/2023 |  |  | BILL/00995/2023-2024 | 461-MSD/2023-24 | 28/12/2023 | 28/12/2023 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.9 | 0 | 0 | 0
15 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of October 2023 |  |  | BILL/00854/2023-2024 | 418-MSD/2023-24 | 07/12/2023 | 07/12/2023 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/08/2023 to 30/09/2023. |  |  | BILL/00721/2023-2024 | 420-MSD/2023-24 | 07/12/2023 | 07/12/2023 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.9 | 0 | 0 | 0
17 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period July 2023 to August 2023. |  |  | BILL/00656/2023-2024 | 418-MSD/2023-24 | 07/12/2023 | 07/12/2023 | R.N CLUB LAB | 0.9 | 0 | 0 | 0
18 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/07/2023 to 31/07/2023 |  |  | BILL/00480/2023-2024 | 420-MSD/2023-24 | 07/12/2023 | 07/12/2023 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
19 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/09/2023 to 30/09/2023. |  |  | BILL/00779/2023-2024 | 421-MSD/2023-24 | 07/12/2023 | 07/12/2023 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
20 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM REMUNERATION OF LAB PERSONNEL FROM JUNE 23 TO AUGUST 23 |  |  | BILL/01005/2023-2024 | 460-MSD/2023-24 | 28/12/2023 | 28/12/2023 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.75 | 0 | 0 | 0
21 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the month of September 2023 to November 2023 |  |  | BILL/00997/2023-2024 | 460-MSD/2023-24 | 28/12/2023 | 28/12/2023 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
22 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM REMUNERATION 01/09/23 TO 30/09/23 |  |  | BILL/00924/2023-2024 | 419-MSD/2023-24 | 07/12/2023 | 07/12/2023 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.45 | 0 | 0 | 0
23 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2023 |  |  | BILL/00998/2023-2024 | 459-MSD/2023-24 | 28/12/2023 | 28/12/2023 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
24 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM OF FESTIVE BONUS 22-23 |  |  | BILL/00925/2023-2024 |  | 05/12/2023 | 05/12/2023 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.16 | 0 | 0 | 0
25 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | REMUNERATION OF LAB PERSONNEL FROM 01/10/23 TO 30/11/23 |  |  | BILL/01004/2023-2024 | 458-MSD/2023-24 | 28/12/2023 | 28/12/2023 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
26 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM REMUNERATION 01/07/23 TO 31/08/2023 |  |  | BILL/00926/2023-2024 | 419-MSD/2023-24 | 07/12/2023 | 07/12/2023 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
27 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period 01/09/2023 to 30/11/2023. |  |  | BILL/00994/2023-2024 | 457-MSD/2023-24 | 28/12/2023 | 28/12/2023 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
28 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Engagement of 01 no. Computer Operator / Data Entry Operator / Customer Service Cell Manager with certificate in computer application on contractual Basis through Agency for District Water Testing Laboratory under the Office of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. For a period of 12 months.(i.e. 01.02.2024 to 31.01.2025) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000793/2023-2024 | 353/MURD | 31/01/2024 | 30/01/2025 | RIZZ ENTERPRISE | 2.25 | 0.8 | 35.37 | 5
29 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Supply & delivery of PT Test Charge for 11 mandatory parameters for 6 nos sub-District water Testing Laboratory as per PT Plan of NABL-139 at least once in a year for Sub Distt Lab & as per PT Plan for District Lab. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000545/2024-2025 | 2095/MURD | 23/07/2024 | 30/07/2024 | M/S LAXMI ENTERPRISE | 0.09 | 0 | 0 | 0
30 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Supply & delivery of 5 nos Tin(II) chloride dihydrate GR(gm), 100 gm pack for Murshidabad District water testing laboratory. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000904/2023-2024 | 266/MURD | 24/01/2024 | 31/01/2024 | M/S LAXMI ENTERPRISE | 0.04 | 0 | 0 | 0
31 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of 02(Two) nos. Chemist (01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) , 02(Two)nos.Bacteriologist(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) and 02(Two)nos. Lab Assitant(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 03(Three) Months. i.e. period form 01/03/2024 to 31/05/2024 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000856/2023-2024 | 610/MURD | 27/02/2024 | 27/05/2024 | BISWAS ENGINEERING & WATER TESTING. | 4.03 | 3.38 | 83.9 | 100
32 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Broad band Net recharge and Sweeping & Cleaning of 11 nos water testing laboratories for one year and arrear for Sweeping & Cleaning of 11 nos water testing laboratories for 12 months under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year. (i.e. period form 01/02/2024 to 31/01/2025) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000806/2023-2024 | 359/MURD | 01/02/2024 | 31/01/2025 | MURARI JHA | 4.49 | 4.49 | 100 | 10
33 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of 07(Seven) nos. Chemist (01 no. District Laboratory and 06nos. Sub-District Laboratory) , 06(Six)nos. Bacteriologist(01 no. District Laboratory and 05nos. Sub-District Laboratory), 11(Eleven)nos. Lab Assitant(01 no. District Laboratory and 10nos. Sub-District Laboratory) and 10(Ten)nos. Sampling Assistant(01 no. District Laboratory and 09nos. Sub-District Laboratory) in each of 11(Eleven) nos. District & Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. for 03(Three) Months. (i.e. period form 01/03/2024 to 31/05/2024) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000855/2023-2024 | 609/MURD | 27/02/2024 | 27/05/2024 | CLIFFORD FACILITY SERVICES PVT. LTD. | 17.32 | 17.32 | 100 | 35
34 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of Three Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/03/2024 to 14/06/2024) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000864/2023-2024 | 772/MURD | 13/03/2024 | 13/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
35 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Payment of month salaries of Chemist , Bacteriologist, Laboratory assistant, Sampling assistant & Data entry operator/CSM for District laboratory and 12 nos sub-district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. For a period of 12 months (i.e. 01.06.2024 to 31.05.2025) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000003/2024-2025 | 1585/MURD | 21/05/2024 | 21/05/2025 | CFS MANAGEMENT PRIVATE LIMITED | 96.96 | 81.19 | 83.73 | 35
36 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Engagement of Chemist and Bacteriologist for water testing laboratories under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year.(i.e. period form 01/03/2024 to 28/02/2025) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000805/2023-2024 | 602/MURD | 27/02/2024 | 26/02/2025 | M/S. S. DAS AND ENTERPRISE | 25.6 | 15.52 | 60.65 | 100
37 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Allied work for Electrification in Murshidabad District Laboratory at Berhampore Under Murshidabad Division PHE Dte .(Electric Portion) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000125/2024-2025 | 2633/MURD | 23/09/2024 | 13/10/2024 | S. DUTTA | 2.57 | 2.57 | 100 | 100
38 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Calibration of measuring Instruments Traceable to standard reference material & as per requirements of NABL guideline for the Equipments required for 11 mandator and other optional parameters(as per NABL 139) & PT Test Charge for 11 mandetaory parameters for Sub-District Water Testing Laboratory as per PT Plan or NABL-139 (Name of the laboratories. 1. Jangipur WTP Sub-District Water Testing Laboratory, 2. Farakka Block Bidi Shramik Kalyan Samity Sub-District Water Testing Laboratory, 3. Gagtai Sub-District Water Testing Laboratory, 4. Joykrishnapur Sub-District Water Testing Laboratory, 5. Sagardighi Sub-District Water Testing Laboratory ) . 6. Mahyampur Water Treatment Plant Sub-District Water Testing Laboratory, 7. CP Cell Sub-District Water Testing Laboratory, 8. Sevabrata Sub-District Water Testing Laboratory, 9. Surangapur Sub-District Water Testing Laboratory) . 10. Rural National Club Sub-District Water Testing Laboratory, 11. Lalbagh Sub-District Water Testing Laboratory, 12. Islampur Sub-District Water Testing Laboratory,13. Jalangi Sub-District Water Testing Laboratory, 14. Berhampore Mechanical Division Sub-District Water Testing Laboratory ) . 15. Haripur Dr. Br Ambedkar Jana Seva Mission Sub-District Water Testing Laboratory, 16. Hariharpara Sub-District Water Testing Laboratory, 17. Rejinagar Sub-District Water Testing Laboratory, 18. Salar Sub-District Water Testing Laboratory) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000103/2024-2025 | 2153/MURD | 29/07/2024 | 01/03/2025 | M/S LAXMI ENTERPRISE | 5.2 | 0 | 0 | 80
39 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Engagement of 1(one) AAS operator/Additional Chemist, 1(one) AAS Sampling Assistant including salary, festival bonus arrear portion of enhanced salary if applicable etc one year technical support for AAS (Thermo Scientific). (For 12 months) (i.e. 01/10/2024 to 30/09/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000129/2024-2025 | 2666/MURD | 25/09/2024 | 25/09/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 6.46 | 0 | 0 | 100
40 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 TO 29/02/2024 |  |  | BILL/01366/2023-2024 | 638-MSD/2023-24 | 17/03/2024 | 17/03/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.01 | 0 | 0 | 0
41 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the period of 01.03.2024 to 31.03.2024 |  |  | BILL/00058/2024-2025 | 52-MSD/2024-25 | 26/04/2024 | 26/04/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
42 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the month of January-2024 |  |  | BILL/01229/2023-2024 | 563-MSD/2023-24 | 21/02/2024 | 21/02/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
43 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Remuneration of Lab Personnel for the month of April 2024 |  |  | BILL/00202/2024-2025 | 132-MSD/2024-25 | 06/06/2024 | 06/06/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.85 | 0 | 0 | 0
44 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Internet recharge of 09 nos. Laboratory under Murshidabad Division, PHE Dte for the month of August 2023 |  |  | BILL/01001/2023-2024 | 516-MSD/2023-24 | 29/01/2024 | 29/01/2024 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
45 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/12/2023 to 31/01/2024 |  |  | BILL/01228/2023-2024 | 565-MSD/2023-24 | 21/02/2024 | 21/02/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
46 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CALIM OF REMUNERATION OF LAB PERSONNEL FROM DECEMBER 2023 TO FEBRUARY 2024 |  |  | BILL/01367/2023-2024 | 634-MSD/2023-24 | 17/03/2024 | 17/03/2024 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
47 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab Personel for the period of 01.12.2023 to 31.01.2024 |  |  | BILL/01241/2023-2024 | 576-MSD/2023-24 | 22/02/2024 | 22/02/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
48 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/06/24 to 30/06/24 |  |  | BILL/00535/2024-2025 | 278-MSD/2024-25 | 12/08/2024 | 12/08/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
49 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the Period 01/06/2024 to 30/06/2024 |  |  | BILL/00540/2024-2025 | 279-MSD/2024-25 | 12/08/2024 | 12/08/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
50 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period 01/10/2024 to 31/10/2024. |  |  | BILL/01531/2024-2025 | 572-MSD/2024-25 | 25/11/2024 | 25/11/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.8 | 0 | 0 | 0
51 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for bonus of Lab personnel for the period 01/09/2024 to 30/09/2024 and festival bonus for the period 2024-2025. |  |  | BILL/01475/2024-2025 | 560-MSD/2024-25 | 30/10/2024 | 30/10/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.63 | 0 | 0 | 0
52 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim of 1st installment of Jal management expenses for the year 2024. |  |  | BILL/01044/2023-2024 | 502-MSD/2023-24 | 17/01/2024 | 17/01/2024 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.4 | 0 | 0 | 0
53 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Bill for Internet Recharge of the Laboratories under Murshidabad Division, PHE Dte for September 2023 |  |  | BILL/01059/2023-2024 | 516-MSD/2023-24 | 29/01/2024 | 29/01/2024 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
54 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the Period 01/12/2023 to 31/12/2023 |  |  | BILL/01042/2023-2024 | 502-MSD/2023-24 | 17/01/2024 | 17/01/2024 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
55 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remmuneration of Lab - Personnel for the period 01/03/2024 to 31/03/2024 |  |  | BILL/00034/2024-2025 | 37-MSD/2024-25 | 19/04/2024 | 19/04/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
56 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of March 2024 and 2nd installment for Lab maintenance of 2023. |  |  | BILL/00072/2024-2025 | 63-MSD/2024-25 | 30/04/2024 | 30/04/2024 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.8 | 0 | 0 | 0
57 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUERATION OF LAB PERSONNEL FOR THE PERIOD 01/04/2024 TO 30/04/2024 |  |  | BILL/00135/2024-2025 | 92-MSD/2024-25 | 22/05/2024 | 22/05/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
58 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month for month of May 2024. |  |  | BILL/00212/2024-2025 | 136-MSD/2024-25 | 12/06/2024 | 12/06/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
59 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2024 to 31/05/2024 |  |  | BILL/00295/2024-2025 | 208-MSD/2024-25 | 02/07/2024 | 02/07/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
60 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab- personnel for the month of September 2024 to November 2024. |  |  | BILL/01607/2024-2025 | 596-MSD/2024-20 | 16/12/2024 | 16/12/2024 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.7 | 0 | 0 | 0
61 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab- Personnel for the period 01/10/2024 to 31/10/2024. |  |  | BILL/01583/2024-2025 | 583-MSD/2024-25 | 06/12/2024 | 06/12/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
62 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 |  |  | BILL/01365/2023-2024 | 637-MSD/2023-24 | 17/03/2024 | 17/03/2024 | RURAL NATIONAL CLUB | 0.61 | 0 | 0 | 0
63 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2024 to 31/05/2024. |  |  | BILL/00296/2024-2025 | 209-MSD/2024-25 | 02/07/2024 | 02/07/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
64 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/10/24 to 30/11/24. |  |  | BILL/01606/2024-2025 | 595-MSD/2024-20 | 16/12/2024 | 16/12/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
65 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2024 |  |  | BILL/01581/2024-2025 | 582-MSD/2024-25 | 06/12/2024 | 06/12/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
66 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2024 |  |  | BILL/01580/2024-2025 | 581-MSD/2024-25 | 06/12/2024 | 06/12/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
67 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of July 2024 |  |  | BILL/00869/2024-2025 | 330-MSD/2024-25 | 30/08/2024 | 30/08/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
68 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of August 2024. |  |  | BILL/01090/2024-2025 | 398-MSD/2024-25 | 20/09/2024 | 20/09/2024 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.45 | 0 | 0 | 0
69 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/12/2023 to 31/12/2023 & 1st installment for the year 2024 of Lab Maintenance |  |  | BILL/01045/2023-2024 | 501-MSD/2023-24 | 17/01/2024 | 17/01/2024 | R.N CLUB LAB | 0.85 | 0 | 0 | 0
70 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period of 01/09/2024 to 30/09/2024 and festive bonus for the year 2024-2025. |  |  | BILL/01299/2024-2025 | 537-MSD/2024-25 | 06/10/2024 | 06/10/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.63 | 0 | 0 | 0
71 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period |  |  | BILL/00871/2024-2025 | 332-MSD/2024-25 | 30/08/2024 | 30/08/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.8 | 0 | 0 | 0
72 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of April 2024 to July 2024. |  |  | BILL/00872/2024-2025 | 333-MSD/2024-25 | 30/08/2024 | 30/08/2024 | COMMUNITY POLITECHNIC SCHEME, MIT | 2.2 | 0 | 0 | 0
73 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of August 2024. |  |  | BILL/01088/2024-2025 | 396-MSD/2024-25 | 20/09/2024 | 20/09/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
74 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Bill for Internet Recharge of the Laboratories under Murshidabad Division, PHE Dte for September 2023 |  |  | BILL/01060/2023-2024 | 516-MSD/2023-24 | 29/01/2024 | 29/01/2024 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
75 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period of 01/01/2024 to 31/01/2024. |  |  | BILL/01227/2023-2024 | 564-MSD/2023-24 | 21/02/2024 | 21/02/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
76 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of September 2024 and festival bonus for the period 2024-2025. |  |  | BILL/01300/2024-2025 | 538-MSD/2024-25 | 06/10/2024 | 06/10/2024 | RURAL NATIONAL CLUB | 0.63 | 0 | 0 | 0
77 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/08/2024 to 31/08/2024. |  |  | BILL/01091/2024-2025 | 399-MSD/2024-25 | 20/09/2024 | 20/09/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
78 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 |  |  | BILL/01363/2023-2024 | 636-MSD/2023-24 | 17/03/2024 | 17/03/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.61 | 0 | 0 | 0
79 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 |  |  | BILL/01364/2023-2024 | 635-MSD/2023-24 | 17/03/2024 | 17/03/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.61 | 0 | 0 | 0
80 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/03/2024 to 31/03/2024 |  |  | BILL/00035/2024-2025 | 35-MSD/2024-202 | 19/04/2024 | 19/04/2024 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
81 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Remuneration of Lab Personnel for the month of April 2024 |  |  | BILL/00138/2024-2025 | 99-MSD/2024-25 | 22/05/2024 | 22/05/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
82 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/09/24 to 30/09/24 and Claim for Festival Bonus of Lab-Personnel for the period 2023-2024. |  |  | BILL/01243/2024-2025 | 536-MSD/2024-25 | 06/10/2024 | 06/10/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.63 | 0 | 0 | 0
83 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of August 2024. |  |  | BILL/01089/2024-2025 | 397-MSD/2024-25 | 20/09/2024 | 20/09/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
84 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Carrying referral water samples to state laboratory. |  |  | BILL/00805/2024-2025 | 329-MSD/2024-25 | 30/08/2024 | 30/08/2024 | M/S. DIPTI ENTERPRISE | 0.07 | 0 | 0 | 0
85 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE MMONTH OF MARCH 2024 |  |  | BILL/00033/2024-2025 | 36-MSD/2024-25 | 19/04/2024 | 19/04/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
86 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/04/24 to 31/05/24. |  |  | BILL/00213/2024-2025 | 135-MSD/2024-25 | 12/06/2024 | 12/06/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
87 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of June 2024 & 2nd installment of lab management expenses in advance for the year 2024. |  |  | BILL/00541/2024-2025 | 280-MSD/2024-25 | 12/08/2024 | 12/08/2024 | RURAL NATIONAL CLUB | 0.8 | 0 | 0 | 0
88 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of October 2024. |  |  | BILL/01533/2024-2025 | 571-MSD/2024-25 | 25/11/2024 | 25/11/2024 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
89 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/06/2024 to 31/07/2024. |  |  | BILL/00870/2024-2025 | 331-MSD/2024-25 | 30/08/2024 | 30/08/2024 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
90 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/07/24 to 31/08/24. |  |  | BILL/01087/2024-2025 | 395-MSD/2024-25 | 20/09/2024 | 20/09/2024 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.25 | 0 | 0 | 0
91 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of Chemist and Bacteriologist for water testing laboratories under Murshidabad Division. P.H.Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year.(i.e. period from 01/03/2025 to 28/02/2026) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000524/2024-2025 | 496/MURD | 27/02/2025 | 27/02/2026 | M/S. S. DAS AND ENTERPRISE | 25.6 | 10.39 | 40.58 | 30
92 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Engagement of 1(one) AAS operator/Additional Chemist, 1(one) AAS Sampling Assistant including salary, festival bonus arrear portion of enhanced salary if applicable etc one year technical support for AAS (Thermo Scientific). (For 11.5 months) (i.e. 01/06/2025 to 15/05/2026) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000084/2025-2026 | 1216/MURD | 27/05/2025 | 27/05/2026 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.62 | 0 | 0 | 0
93 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Payment of monthly salaries of Chemist , Bacteriologist, Laboratory assistant, Sampling assistant & Data entry operator/CSM for District laboratory and 13 nos sub-district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. for one year. (Period form 01/12/2025 to 30/11/2026) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000228/2025-2026 | 2373/MURD | 19/11/2025 | 19/11/2026 | M/S JAN MAHAMMAD | 168.84 | 0 | 0 | 0
94 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Computer Maintenance, UPS Maintenance, Printer maintenance ,Broad band Net recharge, Sweeping ,Cleaning & laboratories maintenance and minor repair of 14 nos water testing laboratories & stationary goods of 14 nos water testing laboratories for one year under Murshidabad Division. P.H. Engineering Dte.(i.e. Period from 01-12-2025 to 30-11-2026) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000229/2025-2026 | 2375/MURD | 19/11/2025 | 19/11/2026 | MURARI JHA | 20.86 | 0 | 0 | 0
95 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Work order for carrying referral water samples to State Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000546/2024-2025 | 14/HQ | 15/01/2025 | 15/01/2026 | M/S. DIPTI ENTERPRISE | 0.1 | 0 | 0 | 100
96 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Continuation work order for Payment of month salaries of Chemist , Bacteriologist, Laboratory assistant, Sampling assistant & Data entry operator/CSM for District laboratory and 12 nos sub-district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. For a period of 06 months (i.e. 01.06.2025 to 30.11.2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000095/2025-2026 | 1148/MURD | 19/05/2025 | 18/11/2025 | CFS MANAGEMENT PRIVATE LIMITED | 43.99 | 0 | 0 | 75
97 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01.12.2024 to 31.12.2024. |  |  | BILL/01798/2024-2025 | 607-MSD/2024-25 | 21/01/2025 | 21/01/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
98 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab -Personal for the period of 01.06.2025 to 30.06.2025. |  |  | BILL/00307/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
99 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of May 2025 to June 2025. |  |  | BILL/00296/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.9 | 0 | 0 | 0
100 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of October 2025. |  |  | BILL/00713/2025-2026 |  | 11/11/2025 | 11/11/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
101 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/04/2025 TO 30/04/2025 |  |  | BILL/00131/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
102 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/09/2025 to 30/09/2025. |  |  | BILL/00731/2025-2026 |  | 17/11/2025 | 17/11/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
103 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of November 2025. |  |  | BILL/00816/2025-2026 |  | 09/12/2025 | 09/12/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
104 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of February 2025. |  |  | BILL/02094/2024-2025 | 703-MSD/24-25 | 28/03/2025 | 28/03/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
105 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remunertion of Lab Personnel for the period 01/04/2025 to 30/04/2025. |  |  | BILL/00133/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
106 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of May 2025. |  |  | BILL/00253/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
107 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/11/2025 to 30/11/2025. |  |  | BILL/00823/2025-2026 |  | 09/12/2025 | 09/12/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
108 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF BACTERIOLOGIST FOR THE MONTH OF MARCH 2025 |  |  | BILL/00064/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.85 | 0 | 0 | 0
109 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/12/24 to 31/01/25. |  |  | BILL/01959/2024-2025 | 625-MSD/24-25 | 18/03/2025 | 18/03/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
110 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/02/2025 TO 28/02/2025. |  |  | BILL/02193/2024-2025 | 784-MSD/2024-25 | 29/03/2025 | 29/03/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
111 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the mont of March 2025 to April 2025 and 1st Intallment of lab maintenance of 2025. |  |  | BILL/00132/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.3 | 0 | 0 | 0
112 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remunerution of Lab personal for the mont of June 2025 and payer for 2nd installment for the year of Lab maintenance Expensed in advance. |  |  | BILL/00308/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | RURAL NATIONAL CLUB | 0.8 | 0 | 0 | 0
113 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/02/2025 to 28/02/2025. |  |  | BILL/02093/2024-2025 | 702-MSD/24-25 | 28/03/2025 | 28/03/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
114 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/06/2025 to 31/06/2025. |  |  | BILL/00310/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
115 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | State level referral cross checking of water samples to Murshidabad District. |  |  | BILL/00298/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | M/S. DIPTI ENTERPRISE | 0.09 | 0 | 0 | 0
116 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/01/2025 TO 31/01/2025. |  |  | BILL/01965/2024-2025 | 627-MSD/24-25 | 18/03/2025 | 18/03/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
117 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the month of December 2024 & 1st installment of lab management expenses in advance for the year 2025. |  |  | BILL/01797/2024-2025 | 606-MSD/2024-25 | 21/01/2025 | 21/01/2025 | RURAL NATIONAL CLUB | 0.85 | 0 | 0 | 0
118 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/02/25 to 31/03/25. |  |  | BILL/00055/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.3 | 0 | 0 | 0
119 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/03/2025 TO 31/03/2025. |  |  | BILL/00056/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
120 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE MONTH OF MARCH 2025 |  |  | BILL/00063/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
121 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of July 2025. |  |  | BILL/00589/2025-2026 | 104/JJM-LAB | 19/09/2025 | 19/09/2025 | RURAL NATIONAL CLUB | 0.33 | 0 | 0 | 0
122 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/11/2025 to 30/11/2025. |  |  | BILL/00817/2025-2026 |  | 09/12/2025 | 09/12/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
123 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of september 2025 to October 2025. |  |  | BILL/00789/2025-2026 |  | 02/12/2025 | 02/12/2025 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.25 | 0 | 0 | 0
124 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2025 to 30/06/2025 and Claim of 2nd installement of lab management expenses for the year 2025 (Kandi Water Testing Laboratory) |  |  | BILL/00311/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 1.25 | 0 | 0 | 0
125 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab - Personnel for the period 01/07/2025 to 31/07/2025 |  |  | BILL/00588/2025-2026 | 104/JJM-LAB | 19/09/2025 | 19/09/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.33 | 0 | 0 | 0
126 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/01/2025 TO 31/01/2025. |  |  | BILL/01956/2024-2025 | 624-MSD/24-25 | 17/03/2025 | 17/03/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
127 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/11/2024 to 30/11/2024 & claim of 1st installment of lab management expenses for the year 2025. |  |  | BILL/01718/2024-2025 | 603-MSD/2024-25 | 13/01/2025 | 13/01/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.85 | 0 | 0 | 0
128 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE MONTH OF JANUARY 2025 |  |  | BILL/01955/2024-2025 | 623-MSD/2024-20 | 17/03/2025 | 17/03/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
129 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE MONTH OF DECEMBER 2024 TO FEBRUARY 2025 |  |  | BILL/02191/2024-2025 | 783-MSD/2024-25 | 29/03/2025 | 29/03/2025 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
130 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2025 to 31/05/2025. |  |  | BILL/00254/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
131 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of April 2025. |  |  | BILL/00134/2025-2026 | 49/LAB/JJM | 14/07/2025 | 14/07/2025 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
132 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/11/2025 to 30/11/2025. |  |  | BILL/00818/2025-2026 |  | 09/12/2025 | 09/12/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
133 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/12/2024 TO 31/12/2024. |  |  | BILL/01820/2024-2025 | 613-MSD/2024-25 | 10/02/2025 | 10/02/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
134 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | State level referral cross checking of water samples to Murshidabad District. |  |  | BILL/01962/2024-2025 | 626-MSD/24-25 | 18/03/2025 | 18/03/2025 | M/S. DIPTI ENTERPRISE | 0.09 | 0 | 0 | 0
135 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/04/2025 to 31/05/2025. |  |  | BILL/00288/2025-2026 | 78/LAB-JJM | 21/08/2025 | 21/08/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
136 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/10/2025 to 31/10/2025. |  |  | BILL/00734/2025-2026 |  | 17/11/2025 | 17/11/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
137 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/10/2025 to 31/10/2025. |  |  | BILL/00759/2025-2026 |  | 21/11/2025 | 21/11/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
138 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab - Personnel for the period 01/07/2025 to 31/07/2025 |  |  | BILL/00590/2025-2026 | 104/JJM-LAB | 19/09/2025 | 19/09/2025 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.33 | 0 | 0 | 0
139 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/07/2025 to 31/07/2025. |  |  | BILL/00591/2025-2026 | 104/JJM-LAB | 19/09/2025 | 19/09/2025 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.33 | 0 | 0 | 0
140 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Chemist for the period 01/12/2025 to 31/12/2025 |  |  | BILL/00864/2025-2026 |  | 03/02/2026 | 03/02/2026 | RURAL NATIONAL CLUB | 0.85 | 0 | 0 | 0
141 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB-PERSONNEL FOR THR MONTH OF April-2026. |  |  | BILL/00175/2026-2027 |  | 29/05/2026 | 29/05/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
142 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/12/2025 to 31/12/2025. |  |  | BILL/00869/2025-2026 |  | 03/02/2026 | 03/02/2026 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
143 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneratin of Bacteriologist for the month of 01/02/2026 to 28/02/2026. |  |  | BILL/01070/2025-2026 |  | 10/03/2026 | 10/03/2026 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
144 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/02/2026 to 28/02/2026 |  |  | BILL/00056/2026-2027 |  | 10/04/2026 | 10/04/2026 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
145 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/05/2026 to 31/07/2026. |  |  | BILL/00412/2026-2027 |  | 19/08/2026 | 19/08/2026 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.35 | 0 | 0 | 0
146 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of May 2026. |  |  | BILL/00240/2026-2027 |  | 23/06/2026 | 23/06/2026 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
147 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/12/2025 to 31/12/2025. |  |  | BILL/00866/2025-2026 |  | 03/02/2026 | 03/02/2026 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
148 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Chemist for the period 01/12/2025 to 31/12/2025 |  |  | BILL/00867/2025-2026 |  | 03/02/2026 | 03/02/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
149 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of January 2026. |  |  | BILL/00890/2025-2026 |  | 09/02/2026 | 09/02/2026 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
150 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/01/2026 to 31/01/2026. |  |  | BILL/00889/2025-2026 |  | 09/02/2026 | 09/02/2026 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
151 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of March 2026 to April 2026. |  |  | BILL/00238/2026-2027 |  | 23/06/2026 | 23/06/2026 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.9 | 0 | 0 | 0
152 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of November 2025 to December 2025. |  |  | BILL/00852/2025-2026 |  | 16/01/2026 | 16/01/2026 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.9 | 0 | 0 | 0
153 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim of 1st installment of lab management expenses for the year 2026 (Kandi water testing laboratory) |  |  | BILL/00868/2025-2026 |  | 03/02/2026 | 03/02/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.4 | 0 | 0 | 0
154 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB-PERSONNEL FOR THR MONTH OF April-2026. |  |  | BILL/00177/2026-2027 |  | 29/05/2026 | 29/05/2026 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
155 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB-PERSONNEL FOR THR MONTH OF MARCH-2026. |  |  | BILL/00015/2026-2027 |  | 06/04/2026 | 06/04/2026 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
156 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneratin of Bacteriologist for the month of February 2026. |  |  | BILL/01072/2025-2026 |  | 10/03/2026 | 10/03/2026 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
157 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Chaim for remuneratin of lab personnel for the month of January 2026 to February 2026. |  |  | BILL/01071/2025-2026 |  | 10/03/2026 | 10/03/2026 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.3 | 0 | 0 | 0
158 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/02/2026 to 28/02/2026. |  |  | BILL/01075/2025-2026 |  | 10/03/2026 | 10/03/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.33 | 0 | 0 | 0
159 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/03/2026 to 30/04/2026 and Appeal for reimbursement of 1-st installment, of laboratory maintenance charge for the year 2026. |  |  | BILL/00241/2026-2027 |  | 23/06/2026 | 23/06/2026 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.3 | 0 | 0 | 0
160 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/05/2026 to 31/05/2026. |  |  | BILL/00239/2026-2027 |  | 23/06/2026 | 23/06/2026 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
161 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/01/2026 TO 31/01/2026. |  |  | BILL/01074/2025-2026 |  | 10/03/2026 | 10/03/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.38 | 0 | 0 | 0
162 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/01/2026 to 31/01/2026. |  |  | BILL/00935/2025-2026 |  | 12/02/2026 | 12/02/2026 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
163 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/03/2026 to 31/03/2026. |  |  | BILL/00014/2026-2027 |  | 06/04/2026 | 06/04/2026 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.38 | 0 | 0 | 0
164 | MURSHIDABAD |  | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | Support-WQMSP | State level referral cross checking of water samples to Murshidabad District |  |  | BILL/01081/2025-2026 |  | 12/03/2026 | 12/03/2026 | M/S. DIPTI ENTERPRISE | 0.07 | 0 | 0 | 0
Total | [13 empty] | 632.34 | 223.36 | 35.32