## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 1210/MURD/07 | 02/05/2023 | 02/05/2023 | Resource Division | 69.83 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000075/2023-2024 | 4306/MEDB | 29/12/2023 | 29/03/2024 | M/S SAMRIDDHI ENTERPRISE | 34.41 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Exsisting Pump House No. I and II under BALLALPUR PIPED WATER SUPPLY SCHEME, BLOCK- FARAKKA, DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000020/2025-2026 | 1144/MEDB | 14/05/2025 | 14/08/2025 | M/S SAMRIDDHI ENTERPRISE | 24.17 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 10.79 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Augmentation of AMINABAD ZONE-I Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000725/2023-2024 | 3952/MURD | 26/12/2023 | 19/12/2025 | M/S GUHA & ROY ENTERPRISE | 446.08 | 0 | 0 | 75
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 100
Total | [13 empty] | 680.82 | 0 | 0