## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III & IV under Hasimpur ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000037/2023-2024 | 1876/MEDB | 16/06/2023 | 16/09/2023 | ABHISEK ENGINEERING CONCERN | 20.73 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 1210/MURD/30 | 02/05/2023 | 02/05/2023 | Resource Division | 158.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Hasimpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000762/2023-2024 | 185/MURD | 18/01/2024 | 01/12/2025 | SAMIRAN KUMAR CHAKRABORTY | 485.31 | 24.23 | 4.99 | 60
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 90 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HASIMPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000019/2025-2026 | 964/MURD | 30/04/2025 | 29/06/2025 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 37.67 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3,JUNIOR ENGINEER 5 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 01/01/2026 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
Total | [13 empty] | 783.05 | 24.23 | 3.09