## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 9.6 | 2.22 | 23.13 | 100
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | NEW CONNECTION AT GARAIMARI Z-II PH-II |  |  | BILL/01137/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 7.33 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | NEW CONNECTION AT GARAIMARI Z-II PH-I |  |  | BILL/01136/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Gairamari ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000660/2023-2024 | 591/MEDB | 31/01/2024 | 04/11/2026 | M/S. SUPER CONSTRUCTION | 36 | 0 | 0 | 70
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | Augmentation of Ground Water Based Garaimari PWSS of accommodate 1468 nos FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 800 CUM OHR, Construction of 250 Cum OHR in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER_DOMKAL BLOCK | ORD/000754/2023-2024 | 120/MURD | 11/01/2024 | 19/10/2025 | M/S R B CONSTRUCTION | 1797.55 | 45.08 | 2.51 | 40
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | Augmentation | Renovation of Filter Media of Existing Modified AIRP of (Capacity 180 Cum/hr.) at Garaimari Zone-I Water Supply Scheme of Domkal Block under Murshidabad Division, P.H.Eengineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000252/2024-2025 | 228/MURD | 27/01/2025 | 13/03/2025 | SOM CONSTRUCTION AGENCY | 28.21 | 0 | 0 | 0
Total | [13 empty] | 1882.7 | 47.3 | 2.51