## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raninagar-II | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 01/12/2022 | MERCHANDISE-INDIA | 14.45 | 2.57 | 17.75 | 90
2 | MURSHIDABAD | Raninagar-II | Berhampore Mechanical | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | New | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 |  |  | BILL/01123/2024-2025 | 267/WBSEDCL-JJM | 28/11/2024 | 28/11/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
3 | MURSHIDABAD | Raninagar-II | Berhampore Mechanical | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | New | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 |  |  | BILL/01116/2024-2025 |  | 25/11/2024 | 25/11/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
4 | MURSHIDABAD | Raninagar-II | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | New | Construction of Ground Water Based Paschim Char Majhardiar PWSS of accommodate FHTC(2246 Nos), Laying Distribution System, Laying Rising Main,Over Head Reservoir ( 500 CUM Capacity), Switch Room, Boundary Wall in Raninagar - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000758/2023-2024 | 140/MURD | 16/01/2024 | 01/01/2026 | M/S. SARKAR CONSTRUCTION | 468.58 | 125.37 | 26.76 | 80
5 | MURSHIDABAD | Raninagar-II | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | New | Allied & Balance Work for Construction of Boundary wall, Land Development ,Road restoration damaged during laying of pipeline, Path Way & Soil Test for Over Head Reservoir of Paschim Char Majhardiar & Adjoining Mouzas Water Supply Scheme in Rani Nagar-I Block of Islampur Sub-Division, under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000195/2024-2025 | 3230/MURD | 10/12/2024 | 14/12/2025 | M/S. SARKAR CONSTRUCTION | 71.53 | 0 | 0 | 0
Total | [13 empty] | 561.36 | 127.94 | 22.79