## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000393/2023-2024 | 714/Rs | 01/03/2024 | 01/01/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 406.91 | 344.84 | 84.75 | 50
2 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000393/2023-2024 | 714/Rs | 01/03/2024 | 01/01/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 406.91 | 344.84 | 84.75 | 50
3 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000364/2023-2024 | 830/RS | 13/03/2024 | 05/11/2024 | IMAGIN | 390.46 | 320.38 | 82.05 | 50
4 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000364/2023-2024 | 830/RS | 13/03/2024 | 05/11/2024 | IMAGIN | 390.46 | 320.38 | 82.05 | 50
5 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000206/2024-2025 | 3173/RS | 30/12/2024 | 30/03/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 130.47 | 27.38 | 20.98 | 99
6 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | Assistant Engineer | Junior Engineer | ORD/000206/2024-2025 | 3173/RS | 30/12/2024 | 30/03/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 130.47 | 27.38 | 20.98 | 99
7 | MURSHIDABAD |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000205/2024-2025 | 3172/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 153.35 | 25.07 | 16.35 | 99
8 | PURBA BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Bardhaman and Murshidabad districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19237 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | Assistant Engineer | Junior Engineer | ORD/000205/2024-2025 | 3172/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 153.35 | 25.07 | 16.35 | 99
Total | [13 empty] | 2162.37 | 1435.32 | 66.38