## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rianpur (Village code 314192) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000202/2020-2021 | 968/BD-I | 17/12/2020 | 17/03/2021 | JAHANGIR ALAM | 38.56 | 38.03 | 98.63 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE,Junior Engineer | ORD/000064/2024-2025 | 1193/BD-I | 25/07/2024 | 21/01/2025 | SOUMEN ADHIKARY | 10.19 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Panisala (Village code 314191) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000200/2020-2021 | 965/BD-I | 17/12/2020 | 17/03/2021 | SAMBHUNATH ROY | 37.24 | 33.5 | 89.94 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | Retrofitting | Additional Laying works at village Rianpur (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Jumra Nayagram ground water supply scheme (Block-Lalgola)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000076/2022-2023 | 632/BD-I | 31/05/2022 | 10/06/2022 | CHATTERJEE ENTERPRISE | 8.92 | 4.55 | 51.05 | 1
Total | [13 empty] | 94.91 | 76.08 | 80.16