## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) | SM/06983 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasbagoas (Village code 314795) under Kasbagoas Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000264/2020-2021 | 338/BD-I | 24/02/2021 | 24/06/2021 | DOBAY CONSTRUCTION | 81.22 | 47.79 | 58.84 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) | SM/06983 | Retrofitting | Additional Laying works at village Kasbagoas (Village code-314795) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Kasbagoas Ground water based Water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer |  | ORD/000796/2021-2022 | 2312/BD-I | 29/12/2021 | 12/02/2022 | BENOY DOBEY | 14.34 | 0 | 0 | 0
Total | [13 empty] | 95.56 | 47.79 | 50.01