## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatpur (Village code 314749) under Hurshi Zone-I Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-11) | Assistant Engineer |  | ORD/000272/2021-2022 | 1143/BD-I | 07/07/2021 | 03/01/2022 | KAMIRUL SK AND CO. | 71.98 | 20.6 | 28.62 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hurshi zone-I ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer |  | ORD/000174/2024-2025 | 2089/BD-I | 22/11/2024 | 22/12/2024 | REDSEA CONSTRUCTION | 3.79 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | Retrofitting | Additional Laying works at village BEGAMPUR (village code 314750) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hurshi Zone-I Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000567/2021-2022 | 1920/BD-I | 08/10/2021 | 18/10/2021 | M/S SAJAHAN CHOWDHURY | 5.99 | 4.59 | 76.57 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314750) under Hurshi Zone-I Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000235/2020-2021 | 69/BD-I | 18/01/2021 | 07/02/2021 | M/S SAJAHAN CHOWDHURY | 17.92 | 13.45 | 75.06 | 75
Total | [13 empty] | 99.67 | 38.64 | 38.76