## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Additional laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna for the village of Hasanpur (Habitation Id-0001294589) at village of Hasanpur (Village Code-314405) under Hasanpur Ground Water Supply Scheme (Bhagawangola-II Block) under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000006/2022-2023 | 548/BD-I | 13/05/2022 | 23/05/2022 | JAHANGIR ALAM | 2.83 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under HASANPUR ground Water based Water Supply Scheme of Bhagawangola-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I |  | ORD/000272/2023-2024 | 976/BD-I | 18/10/2023 | 16/01/2024 | PRAVAT KUMAR GHOSH | 11.83 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 314536) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. |  | JE_RAJIB BISWAS | ORD/000199/2020-2021 | 964/BD-I | 17/12/2020 | 15/02/2021 | M/S J.A CONSTRUCTION | 4.46 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasanpur (Habitation ID-0001294589 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000196/2020-2021 | 967/BD-I | 17/12/2020 | 17/03/2021 | JAHANGIR ALAM | 21.8 | 0 | 0 | 35
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur and Others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I |  | ORD/000113/2021-2022 | 915/BD-I | 19/05/2021 | 26/05/2021 | M/S J.A CONSTRUCTION | 0.77 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Alaipur (village code 314537) under HASANPUR Ground water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000746/2021-2022 | 2260/BD-I | 22/12/2021 | 11/01/2022 | KUNTAL SAHA | 6.91 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hasanpur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000079/2024-2025 | 1227/BD-I | 29/07/2024 | 27/09/2024 | M/S JOY MA BANAMALI | 15.89 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shibnagar (Habitation ID-0001294590 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000197/2020-2021 | 975/BD-I | 17/12/2020 | 17/03/2021 | KAMIRUL SK AND CO. | 24.37 | 15.54 | 63.76 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur and others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000208/2020-2021 | 275/ BD-I | 15/02/2021 | 25/02/2021 | SWARUP KUMAR BHATTA | 2.26 | 0 | 0 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (Village code 314510) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000198/2020-2021 | 963/BD-I | 17/12/2020 | 15/02/2021 | SWARUP KUMAR BHATTA | 8.42 | 0 | 0 | 1
Total | [13 empty] | 99.54 | 15.54 | 15.61