## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | SM/07221 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadhukhali (Village code 315672) under Sadhukhali Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer-II | Junior Engineer-II | ORD/000427/2021-2022 | 1635/BD-I | 02/09/2021 | 01/03/2022 | TARUN KUMAR BHATTACHARYA | 51.96 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | SM/07221 | Retrofitting | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II |  | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 13/03/2022 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | SM/07221 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000111/2024-2025 | 1447/BD-I | 04/09/2024 | 19/09/2024 | KALAM SK | 0.99 | 0 | 0 | 0
Total | [13 empty] | 69.12 | 0 | 0