## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | SM/07223 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Komnagar (Village code 314572) under Komnagar Ground Water Supply Scheme in Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer | Junior Engineer-II | ORD/000441/2021-2022 | 968/BD-I | 07/06/2021 | 04/12/2021 | S.P CONSTRUCTION | 49.3 | 34.35 | 69.68 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | SM/07223 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Komnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000083/2024-2025 | 1244/BD-I | 30/07/2024 | 29/08/2024 | R.S. CONSTRUCTION | 9.36 | 0 | 0 | 0
Total | [13 empty] | 58.66 | 34.35 | 58.56