## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | SM/07224 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Udaynagar Diar (Village code 314613) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000181/2020-2021 | 918/BD-I | 10/12/2020 | 10/03/2021 | M/S S.DAS & ENTERPRISE | 34.84 | 39.5 | 113.36 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | SM/07224 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Azimpur (Village code 314612) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 - 2021,SL-01). | Assistant Engineer | JE | ORD/000240/2020-2021 | 73 /BD-I | 19/01/2021 | 08/02/2021 | M/S ROY & BOSE ENTERPRISE | 7.67 | 6.18 | 80.58 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | SM/07224 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Udaynagar Diar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000173/2024-2025 | 2038/BD-I | 12/11/2024 | 16/01/2026 | SHIV SHAKTI CONSTRUCTION | 9.1 | 0 | 0 | 100
Total | [13 empty] | 51.61 | 45.68 | 88.5