## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | SM/07227 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hazi Mahammadpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000129/2024-2025 | 1479/BD-I | 06/09/2024 | 05/11/2024 | MURSHID ALOM | 11.94 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | SM/07227 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Hazi Mahammadpur ( Habitation ID: 0001294220) in the village of Hazi Mahammadpur (Village code 314231) under Hazi Mahammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2020-2021 | 1048/BD-I | 28/12/2020 | 28/03/2021 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.81 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | SM/07227 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Dakshin Ashariadaha (Village code 314229) under Hazi Mohammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-16 of 2020 ¿ 2021,SL-10) | Assistant Engineer-I | JE | ORD/000243/2020-2021 | 76/BD-I | 19/01/2021 | 18/02/2021 | JIBENDRA NARAYAN SUKUL | 24.9 | 19.18 | 77.03 | 0
Total | [13 empty] | 69.65 | 19.18 | 27.54