## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of DakshinGopalpur (Village code 314797) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-06 of 2020 ¿ 2021,SL-06) | Assistant Engineer | Junior Engineer-II | ORD/000381/2021-2022 | 1465/BD-I | 16/08/2021 | 15/09/2021 | DOBAY CONSTRUCTION | 44.57 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Dakshin Gopalpur ground Water based Water Supply Scheme under Raninagar -I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000108/2023-2024 | 437/BD-I | 12/07/2023 | 10/10/2023 | SOMNATH DEY | 2.32 | 0 | 0 | 75
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Dakhsin Gopalpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000071/2024-2025 | 1219/BD-I | 29/07/2024 | 27/09/2024 | CHATTERJEE ENTERPRISE | 15.96 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gajepara (Village code 314796) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000180/2020-2021 | 829/BD-I | 13/11/2020 | 12/01/2021 | M/S SAJAHAN CHOWDHURY | 20.51 | 13.55 | 66.05 | 0
Total | [13 empty] | 83.36 | 13.55 | 16.25