## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) | SM/07230 | Retrofitting | Formal Work Order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nalbatta (Village code 314801) under Kasbagoas Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-09) | Assistant Engineer | Junior Engineer-II | ORD/000425/2021-2022 | 1598/BD-I | 31/08/2021 | 27/02/2022 | NOVELTY CONSTRUCTION | 58.29 | 46.21 | 79.28 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) | SM/07230 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000073/2024-2025 | 1221/BD-I | 29/07/2024 | 27/09/2024 | SWARUP KUMAR BHATTA | 14.97 | 0 | 0 | 0
Total | [13 empty] | 73.26 | 46.21 | 63.07