## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | SM/07232 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramchandrapur (Village code 314592) under Ramchandrapur Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000221/2020-2021 | 985/BD-I | 17/12/2020 | 15/02/2021 | SOM CONSTRUCTION AGENCY | 16.15 | 19.07 | 118.06 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | SM/07232 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Ramchandrapur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000141/2024-2025 | 1607/BD-I | 03/10/2024 | 02/11/2024 | SUJIT CHOWDHURY | 5.13 | 0 | 0 | 0
Total | [13 empty] | 21.28 | 19.07 | 89.59