## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | Retrofitting | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 12/02/2022 | BIJOY CHOWDHURY | 13.36 | 2.47 | 18.45 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | Retrofitting | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur and others under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000412/2021-2022 | 1441/BD-I | 11/08/2021 | 21/08/2021 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 1.16 | 0.73 | 62.92 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314214) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-I | JE | ORD/000179/2020-2021 | 828/BD-I | 13/11/2020 | 12/01/2021 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 10.28 | 12.88 | 125.34 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000081/2024-2025 | 1233/BD-I | 30/07/2024 | 28/09/2024 | PRIME CONSTRUCTION | 28.06 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egdalia(Village code 314213) under Bajipur Madhupur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000098/2020-2021 | 165/BD-I | 03/02/2021 | 23/02/2021 | LAXMI CONSTRUCTION | 4.93 | 9.48 | 192.29 | 1
Total | [13 empty] | 57.79 | 25.56 | 44.22