## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 142/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 4.56 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | Retrofitting | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Hanumantanagar (Village code 314436) under Dakshin Hanumantanagar Ground Water based Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE | ORD/000384/2021-2022 | 1488/BD-I | 18/08/2021 | 14/02/2022 | H.I ENTERPRISE | 217.42 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | Retrofitting | Additional Laying works at village Dakhshin Hanumantanagar (Village code-314436) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Dakhshin Hanumantanagar Ground water based Water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE | ORD/000795/2021-2022 | 2311/BD-I | 29/12/2021 | 27/02/2022 | H.I ENTERPRISE | 30.49 | 0 | 0 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000095/2024-2025 | 1307/BD-I | 07/08/2024 | 06/10/2024 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 28.84 | 0 | 0 | 0
Total | [13 empty] | 281.31 | 0 | 0