## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) | SM/07693 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara Foridpur (Village code 315664) under Rampara Foridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2020-2021 | 184/BD-I | 04/02/2021 | 06/03/2021 | DOBAY CONSTRUCTION | 98.77 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) | SM/07693 | Retrofitting | Additional Laying works at village Rampara Foridpur (Village code-315664) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rampara Foridpur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II |  | ORD/000794/2021-2022 | 2310/BD-I | 29/12/2021 | 12/02/2022 | BENOY DOBEY | 15.18 | 0 | 0 | 0
Total | [13 empty] | 113.95 | 0 | 0