## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | SM/07694 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Charkamnagar (Village code 315620),Nagar (Village code 315622),Maklishpur (Village code 315623) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-II | ORD/000208/2021-2022 | 1006/BD-I | 21/06/2021 | 21/07/2021 | KAMIRUL SK AND CO. | 69.19 | 37.16 | 53.71 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | SM/07694 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000115/2024-2025 | 1450/BD-I | 04/09/2024 | 03/11/2024 | SUDIPA SINGHA ROY | 13.53 | 0 | 0 | 0
Total | [13 empty] | 82.71 | 37.16 | 44.93