## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | SM/07698 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khemrajpur (Village code 314761),Naodapara (Village code 314763),Srirampur(Village code 314762) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000123/2020-2021 | 199/BD-I | 04/02/2021 | 06/03/2021 | M/S S.S ENTERPRISE | 71.38 | 25.99 | 36.41 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | SM/07698 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer |  | ORD/000075/2024-2025 | 1223/BD-I | 29/07/2024 | 27/09/2024 | M/S. MONDAL ENTERPRISE | 23.39 | 0 | 0 | 0
Total | [13 empty] | 94.76 | 25.99 | 27.43