## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | SM/07705 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rajarampur (Village code 314196) under Rajarampur Ground Water based Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) (Sl-05) | Assistant Engineer-I | JE | ORD/000293/2021-2022 | 1134/BD-I | 06/07/2021 | 02/01/2022 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 104.87 | 109.88 | 104.77 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | SM/07705 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidabad District Under Berhampore Division-I,PHE Dte. in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 1446/BD-I | 04/09/2024 | 03/11/2024 | PRANAB KUMAR GHOSH | 32.27 | 0 | 0 | 0
Total | [13 empty] | 137.14 | 109.88 | 80.12