## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) | SM/07714 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of BAUSI (Village code 314208) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE,JE_RAJIB BISWAS | ORD/000149/2020-2021 | 266/ BD-I | 12/02/2021 | 11/08/2021 | M/S JOGMAYA ENTERPRISE | 62.05 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) | SM/07714 | Retrofitting | Additional Laying works at village Bausi to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE,JE_RAJIB BISWAS | ORD/000843/2021-2022 | 99/BD-I | 01/02/2022 | 21/02/2022 | M/S JOGMAYA ENTERPRISE | 23.01 | 0 | 0 | 100
Total | [13 empty] | 85.06 | 0 | 0