## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | SM/07721 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-II |  | ORD/000170/2022-2023 | 1385/BD-I | 23/12/2022 | 23/12/2023 | SEBAYAN CONSTRUCTION | 1.81 | 3.17 | 174.78 | 71
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | SM/07721 | Retrofitting | Additional Laying works at village DAKATIAPOTA( Village code-315523) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bali Zone-I Ground water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | JE | ORD/000570/2021-2022 | 1922/BD-I | 08/10/2021 | 18/10/2021 | KAMIRUL SK AND CO. | 5.29 | 5.19 | 98.28 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | SM/07721 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakatiapota (Village code 315523) under Bali Zone-I Ground Water based Water Supply Scheme for Nawda Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000130/2020-2021 | 206/BD-I | 04/02/2021 | 24/02/2021 | KAMIRUL SK AND CO. | 33.13 | 55.07 | 166.24 | 1
Total | [13 empty] | 40.23 | 63.44 | 157.69