## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | SM/07724 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mathbarenda (Village code 314480) , Patti Bahadurpur (Village code 314489) Sultanpur (Village code 314490),Madapur (Village code 314482) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000100/2020-2021 | 166/BD-I | 03/02/2021 | 05/03/2021 | DECON INDIA | 80.84 | 66.39 | 82.12 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | SM/07724 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000109/2024-2025 | 1444/BD-I | 04/09/2024 | 03/11/2024 | BHOWMIK CONSTRUCTION | 18.28 | 0 | 0 | 100
Total | [13 empty] | 99.12 | 66.39 | 66.98