## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) | SM/07731 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Basantapur(Village code 314446),Lalitakuri(Village code 314449) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000107/2020-2021 | 173/BD-I | 03/02/2021 | 05/03/2021 | DECON INDIA | 76.45 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) | SM/07731 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000132/2024-2025 | 1530/BD-I | 19/09/2024 | 18/11/2024 | HAFIZUL SEIKH | 17.26 | 0 | 0 | 0
Total | [13 empty] | 93.71 | 0 | 0