## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba | SM/07784 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ilimpur (Village code 314175) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000139/2020-2021 | 239/BD-I | 10/02/2021 | 09/08/2021 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 66.88 | 61.35 | 91.73 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba | SM/07784 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidabad District" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000104/2024-2025 | 1436/BD-I | 04/09/2024 | 04/10/2024 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 15.6 | 0 | 0 | 0
Total | [13 empty] | 82.48 | 61.35 | 74.38