## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | SM/07786 | Retrofitting | Additional of different dia of UPVC pipeline for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur (Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000415/2021-2022 | 1453/BD-I | 13/08/2021 | 23/08/2021 | KAMIRUL SK AND CO. | 1.03 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | SM/07786 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur(Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000109/2020-2021 | 176/BD-I | 03/02/2021 | 23/02/2021 | KAMIRUL SK AND CO. | 12.76 | 9.51 | 74.5 | 1
Total | [13 empty] | 13.79 | 9.51 | 68.93