## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | SM/07787 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Karttikpur(Village code 314220) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000128/2020-2021 | 204/BD-I | 04/02/2021 | 06/03/2021 | SARAJIT KUMAR MAJUMDAR | 61.23 | 45.46 | 74.25 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | SM/07787 | Retrofitting | Laying of different dia UPVC Pipeline for uncovered Habitation and damage portion at Bansgara Ground Water based Water Supply Scheme under Lalgola Block under Berhampore Division-I ,P.H.E Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000426/2021-2022 | 1634/BD-I | 02/09/2021 | 02/10/2021 | SANTA TRADING | 18.56 | 18.79 | 101.23 | 1
Total | [13 empty] | 79.79 | 64.25 | 80.52