## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) | SM/07792 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saralpur (Village code 314538) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000232/2020-2021 | 38/BD-I | 13/01/2021 | 13/04/2021 | JAHANGIR ALAM | 41.33 | 32.43 | 78.48 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) | SM/07792 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Debaipur (Village code 314548) under Benipur Ground Water based Water Supply Scheme for Bhagwangola- II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000224/2020-2021 | 988/BD-I | 17/12/2020 | 17/03/2021 | DOBAY CONSTRUCTION | 37.11 | 54.62 | 147.19 | 0
Total | [13 empty] | 78.44 | 87.05 | 110.98