## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kharsadanga, Putijol, Sundhipur & Rajdharpara (Village code 315377, 315395, 315371 & 315375) respectively under Purba Narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000142/2020-2021 | 242/BD-I | 10/02/2021 | 09/08/2021 | MADE & TRADE CO. | 306.14 | 116.98 | 38.21 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda Panur, Tarakpur, Kaya & Purba Narayanpur (Village code 315378, 315380, 315379 & 315376) under Purba narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000143/2020-2021 | 249/BD-I | 11/02/2021 | 10/08/2021 | J.D.J ENTERPRISE | 393.6 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 0 | 0 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gopinathpur (Village code 315393) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2020-2021 | 296/BD-I | 19/02/2021 | 21/03/2021 | M/S BIMALENDU BOSE | 9.59 | 0 | 0 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kariagachhi (Village code 315394) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000159/2020-2021 | 297/BD-I | 19/02/2021 | 21/03/2021 | A.P CONSTRUCTION | 7.15 | 0 | 0 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Uday Nagar (village code 315396) , Gar Baharampur ( village code 315388 ) and Pakuria ( village code 315381 ) under PURBONARAYANPUR ( Zone - B ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000464/2021-2022 | 1836/BD-I | 05/10/2021 | 14/12/2021 | HOQUEDAR ALI | 58.64 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Additional Laying works at village Kharsadanga, Putijol,Sundhipur and Rajdharpara (Village code-315377,315395,315371 and 315375) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Purba Narayanpur (Zone-B)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000791/2021-2022 | 2302/BD-I | 28/12/2021 | 28/03/2022 | SOUNAK ENTERPRISE | 73.56 | 0 | 0 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Supply of safe drinking water by laying of pipe line at Tikiapara primary school ,Madapur Adibasi Junior High School and Nagrajal High School with arrangement of safe drinking water from surface water based water supply scheme ,Central sector Part-II (Hatinagar and Purbonarayanpur as per zone) at Tikiapara P.S and Madapur P.S. in connection with JJM (Jal Jeevan Mission) under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000021/2023-2024 | 92/BD-I | 03/05/2023 | 02/06/2023 | MAA CONSTRUCTION | 2.82 | 0 | 0 | 100
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | Retrofitting | Allied work for the work of Improvement of Distribution piped water line for providing drinking water facility to the local habitation within command area of Purbo Narayanpur Water supply scheme (Central Sector, Part-II) under Berhampore Division-I,PHE Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000124/2024-2025 | 1472/BD-I | 06/09/2024 | 05/03/2025 | SARAJIT KUMAR MAJUMDAR | 21.24 | 0 | 0 | 50
Total | [13 empty] | 1005.19 | 116.98 | 11.64