## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SRIPUR (Village code 315511) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000148/2020-2021 | 265/ BD-I | 12/02/2021 | 11/08/2021 | MS RUBIET HOSSAIN | 107.3 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 2096/BD-I/8 | 25/11/2024 | 25/11/2024 | Resource Division | 24.64 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of GAZNIPUR (Village code 315512)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000146/2020-2021 | 261/ BD-I | 12/02/2021 | 11/08/2021 | RAJ KUMAR MONDAL | 78.63 | 39.55 | 50.3 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of PADMANABHPUR (Village code 315507)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000147/2020-2021 | 264/ BD-I | 12/02/2021 | 11/08/2021 | SARAJIT KUMAR MAJUMDAR | 113.25 | 0 | 0 | 80
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village of Joykrishnapur (Village code 315508) under Choa (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000145/2020-2021 | 252/BD-I | 11/02/2021 | 12/05/2021 | DOBAY CONSTRUCTION | 42.77 | 0 | 0 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahajadpur (Village code 315513) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000138/2020-2021 | 238/BD-I | 10/02/2021 | 09/08/2021 | M/S UNIVERSAL TRADING | 91.12 | 0 | 0 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Additional and balance work of HDPE pipe for house service connection and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna from Choa Thana more towards Sahebnagar & Tangramari Village and at Borakhali village and Pirtala village of Choa G.P of Choa Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000578/2021-2022 | 1847/BD-I | 07/10/2021 | 26/11/2021 | M/S RUBIET HOSSAIN | 44.49 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of CHOA (Village code 315510) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000247/2020-2021 | 977/BD-I | 17/12/2020 | 15/06/2021 | MS RUBIET HOSSAIN | 240.3 | 96.25 | 40.05 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | Retrofitting | Additional Laying works at village GAZNIPUR ( Village code-315512) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Choa (Zone-F) Surface water supply scheme of Central Sector Part-II (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000785/2021-2022 | 2289/BD-I | 28/12/2021 | 17/01/2022 | RAJ KUMAR MONDAL | 12.42 | 0 | 0 | 1
Total | [13 empty] | 887.37 | 135.8 | 15.3