## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naopara,Simulia and Panch Baria (Village code 315372,315373,315374) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000249/2021-2022 | 1028/BD-I | 21/06/2021 | 09/09/2021 | M/S JHA CONSTRUCTION | 76.94 | 18.86 | 24.51 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekpara and Jagannathpur (Village code 315472,315477) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000250/2021-2022 | 1030/BD-I | 21/06/2021 | 19/09/2021 | NEOGI ENTERPRISE | 87.92 | 59.34 | 67.49 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lal Nagar and Bil Bhandardaha (Village code 315471,315473) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000251/2021-2022 | 1031/BD-I | 21/06/2021 | 19/09/2021 | SUBHAS CHANDRA KESHARI | 86.54 | 42.48 | 49.08 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baruipara (Village code 315465) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2021-2022 | 1033/BD-I | 21/06/2021 | 30/08/2021 | DECON INDIA | 62.7 | 21.06 | 33.58 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahishmara (Village code 315474) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000229/2021-2022 | 1027/BD-I | 21/06/2021 | 10/08/2021 | SARAJIT KUMAR MAJUMDAR | 42.39 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara and Bhandardaha (Village code 315475,315476) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2021-2022 | 1029/BD-I | 21/06/2021 | 30/08/2021 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 65.72 | 85.65 | 130.33 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 6.3 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khidirpur & Simulia Jot (Village code 315466) under Pradipdanga (Zone-H)Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-II | Junior Engineer-II | ORD/000424/2021-2022 | 1595/BD-I | 31/08/2021 | 27/02/2022 | NAYLA CONSTRUCTION | 105.36 | 91.58 | 86.93 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kismat Imadpur (Village code 315468) under Pradipdanga (Zone-H) Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer-II |  | ORD/000497/2021-2022 | 1904/BD-I | 08/10/2021 | 06/04/2022 | MS RUBIET HOSSAIN | 176.97 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Pradipdanga Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000756/2021-2022 | 2222/BD-I | 15/12/2021 | 15/03/2022 | APURBA SAHA CHOWDHURY | 82.14 | 79.33 | 96.58 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamalpur and Pradipdanga (Village code 315469,315470) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000252/2021-2022 | 1032/BD-I | 21/06/2021 | 30/08/2021 | M/S AMIT KUMAR GUPTA | 69.96 | 26.19 | 37.44 | 60
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Additional Laying works at village Jamalpur and Pradipdanga (Village code-315469 and 315470) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Pradipdanga Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000786/2021-2022 | 2290/BD-I | 28/12/2021 | 17/01/2022 | M/S AMIT KUMAR GUPTA | 12.67 | 8.95 | 70.63 | 1
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Pradipdanga(Zone-H) Surface Water based Water Supply Scheme of Central Sector (Part-II) under Hariharpara Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II |  | ORD/000112/2023-2024 | 441/BD-I | 12/07/2023 | 10/10/2023 | S DUTTA | 48.85 | 0 | 0 | 0
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II) Under Hariharpara Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000159/2024-2025 | 1647/BD-I | 23/10/2024 | 22/04/2025 | NOVELTY CONSTRUCTION | 68.93 | 0 | 0 | 70
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 30.06.2025. | Assistant Engineer-II | JE | ORD/000273/2024-2025 | 2335/BD-I | 30/12/2024 | 30/06/2025 | SEBAYAN CONSTRUCTION | 0.91 | 2.4 | 264.14 | 0
16 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.07.2025 to 31.10.2025. | Assistant Engineer-II | JE | ORD/000092/2025-2026 | 855/BD-I | 30/06/2025 | 31/10/2025 | SEBAYAN CONSTRUCTION | 0.6 | 0 | 0 | 0
Total | [13 empty] | 1121.05 | 444.17 | 39.62