## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raipur (Village code 315460) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-II | Junior Engineer-II | ORD/000270/2021-2022 | 1141/BD-I | 07/07/2021 | 03/01/2022 | M/S JOYDEEP DASGUPTA | 79 | 73.28 | 92.76 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 6.3 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Masurdanga ( village code 315464 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000463/2021-2022 | 1838/BD-I | 05/10/2021 | 14/12/2021 | NIRMAL UDYOG | 62.56 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Relaying of different dia DI and UPVC distribution Pipe Line instead of damage portion in between different node point for faciliating FHTC works under Raipur Surface based Water Supply Scheme under Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000561/2021-2022 | 1989/BD-I | 01/11/2021 | 01/12/2021 | DEBASIS BOSE | 31.04 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jitarpur (village code 315461) , Harishpur (village code 315462) , Khosalpur ( village code 315463 ) , under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000465/2021-2022 | 1837/BD-I | 05/10/2021 | 14/12/2021 | HOQUEDAR ALI | 61.23 | 41.59 | 67.94 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur ( village code 315482 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000466/2021-2022 | 1839/BD-I | 05/10/2021 | 14/11/2021 | PARTHA PRATIM DAS | 35.44 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bainpur, Balarampur, Khalshi, Saharbasa, Mamlatpur, Chhota Saharbasa, Hosenpur, Jamira, Fatepur-Gobindapur & Kumipur Patharghata (Village code 315454, 315455, 315456, 315457, 315458, 315459, 315485, 315486, 315487 & 315488) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Hariharpara Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-II | Junior Engineer-II | ORD/000585/2021-2022 | 2012/BD-I | 08/11/2021 | 07/05/2022 | SANJAY BISWAS | 130.03 | 89.24 | 68.63 | 85
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dasturpara (Village code 315484) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-03) | Assistant Engineer-II | Junior Engineer-II | ORD/000559/2021-2022 | 1891/BD-I | 07/10/2021 | 05/04/2022 | M/S S.DAS & ENTERPRISE | 75.05 | 63.52 | 84.64 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Raipur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000775/2021-2022 | 2255/BD-I | 21/12/2021 | 21/03/2022 | M/S GHOSH ENTERPRISE | 77.39 | 75.21 | 97.18 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Laying of additional extension and parallel pipe line at Mamdalipur,Raipur and Sadananpur village due to smooth functioning of Functional Household Tap Connection (FHTC) at RAIPUR Surface Water based Water Supply Scheme of Central Sector Part - II of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000494/2021-2022 | 1881/BD-I | 07/10/2021 | 05/01/2022 | M/S JOYDEEP DASGUPTA | 36.18 | 32.68 | 90.33 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hariharpara, Bochadanga, & Gobindapur (Village code 315483, 315452 & 315453) under RAIPUR (Zone-D) Water Supply Scheme of Central Sector Part-II inHariharpara of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000845/2021-2022 | 101/BD-I | 01/02/2022 | 31/07/2022 | J.D.J ENTERPRISE | 246.75 | 0 | 0 | 0
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Additional Laying works at village Dasturpara (Village code-315484) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Raipur Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000850/2021-2022 | 106/BD-I | 01/02/2022 | 03/03/2022 | M/S S.DAS & ENTERPRISE | 24.15 | 16.64 | 68.9 | 1
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 62/BD-I | 27/01/2022 | 27/01/2022 | Resource Division | 7.67 | 0 | 0 | 0
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 70/BD-I | 28/01/2022 | 28/01/2022 | Resource Division | 2.48 | 0 | 0 | 0
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 2096/BD-I/9 | 25/11/2024 | 25/11/2024 | Resource Division | 24.64 | 0 | 0 | 0
Total | [13 empty] | 1026.05 | 400.52 | 39.03