## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of RUKUNPUR (Village code 315481) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000077/2020-2021 | 976/BD-I | 17/12/2020 | 15/06/2021 | PRADIP KUMAR DAS | 235.52 | 246.56 | 104.69 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 2096/BD-I/10 | 25/11/2024 | 25/11/2024 | Resource Division | 12.32 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (Village code 315480) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE,Junior Engineer-II | ORD/000133/2020-2021 | 232/BD-I | 10/02/2021 | 27/07/2026 | M/S GOUTAM CHAKRABORTY | 130.13 | 103.4 | 79.46 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Biharia (Village code 315478) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000137/2020-2021 | 237/BD-I | 10/02/2021 | 09/08/2021 | UNIVERSAL CONSTRUCTION | 160.94 | 154.25 | 95.84 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JE_RAJIB BISWAS,Junior Engineer-II | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 13/01/2022 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 53.67 | 56.46 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tehatta (village code 315479) under RUKUNPUR ( Zone - G ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2021-2022 | 1835/BD-I | 05/10/2021 | 04/12/2021 | PARTHA PRATIM DAS | 49.71 | 26.51 | 53.32 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer-II | JE | ORD/000377/2023-2024 | 1282/BD-I | 27/12/2023 | 27/12/2024 | SEBAYAN CONSTRUCTION | 1.81 | 4.79 | 264.03 | 30
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Additional and balance work of HDPE pipe for house service connection for retrofitting FHTC and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna under command area of village Rukunpur ( village code-315481 ) under Rukunpur (Zone -G )Surface Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000577/2021-2022 | 1846/BD-I | 07/10/2021 | 06/12/2021 | DAS TRADING CO | 50.67 | 50.64 | 99.94 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Laying of different dia UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion and Rukunpur Satsang Kandra with alied works of Rukunpur (Zone-G) based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-II |  | ORD/000015/2023-2024 | 86/BD-I | 03/05/2023 | 02/06/2023 | CHATTERJEE ENTERPRISE | 2.89 | 2.81 | 97.12 | 100
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Additional work of providing retrofitting functional household tap connetion (FHTC) in connection with JJM and Jal Swapna under command area of village Tehatta (village code 315479) under Rukunpur (Zone-G) surface water based water supply scheme of central sector part-II under Berhampore Division-I PHE Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000385/2023-2024 | 147/BD-I | 05/02/2024 | 05/04/2024 | PARTHA PRATIM DAS | 3.36 | 3.34 | 99.46 | 100
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | Retrofitting | Interconnection between delivery of OHR main and distribution system at OHR site and construction of different dia sluice valve chamber under Rukunpur water supply scheme of central sector part-II under JJM under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE | ORD/000444/2023-2024 | 443/BD-I | 15/03/2024 | 14/04/2024 | CHATTERJEE ENTERPRISE | 1.94 | 1.73 | 89.09 | 50
Total | [13 empty] | 876.82 | 655.37 | 74.74