## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 6.3 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Beniagram Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer-I | ORD/000762/2021-2022 | 2228/BD-I | 15/12/2021 | 15/03/2022 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 71 | 68.22 | 96.09 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 145/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 18.66 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Beniagram (Village code 313832) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer | Junior Engineer-I | ORD/000584/2021-2022 | 2011/BD-I | 08/11/2021 | 07/05/2022 | M/S S.DAS & ENTERPRISE | 162.77 | 0 | 0 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chauki, Kashinagar, Samaspur & Imamnagar (Village code 313803, 313806, 313810 & 313815) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer | Junior Engineer-I | ORD/000615/2021-2022 | 2050/BD-I | 17/11/2021 | 05/05/2024 | DOBAY CONSTRUCTION | 142.86 | 118.84 | 83.19 | 80
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur, Asua, Hosenpur & Jafarganj (Village code 313816, 313817, 313818 & 313809) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer | Junior Engineer-I | ORD/000583/2021-2022 | 2010/BD-I | 08/11/2021 | 21/03/2025 | DECON INDIA | 167.27 | 134.55 | 80.44 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer | Junior Engineer-I | ORD/000379/2023-2024 | 1281/BD-I | 27/12/2023 | 27/12/2024 | TARUN KUMAR BHATTACHARYA | 1.81 | 3.94 | 217.28 | 33
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Relaying of different dia UPVC Pipe line in connection with JJM (Jal Jeevan Mission) over damaged portion and Interconnection between over flow line and Delivery Line at Beniagram Zone-II OHR Site under Beniagram Surface Based water supply scheme of Zone-II of Murshidabad District under Berhampore Division-I PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000019/2023-2024 | 90/BD-I | 03/05/2023 | 02/06/2023 | BABAI GHOSH | 3.05 | 3.01 | 98.72 | 100
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Beniagram & its adjoining Mouzas Surface Water based Water Supply Scheme of Farakka Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | JE | ORD/000110/2023-2024 | 439/BD-I | 12/07/2023 | 10/10/2023 | CHAND ENTERPRISE | 2.32 | 2.15 | 93.03 | 100
Total | [13 empty] | 702.17 | 339.06 | 48.29