## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000114/2024-2025 | 1434/BD-I | 04/09/2024 | 03/11/2024 | MOLLA ENTERPRISE | 34.65 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangapur, Binkar, Mahisasthali, Gopinathpur, Gopalpur & Pulinda (Village code 315562, 315563, 315564, 315565, 315566 & 315567) under Gopinathpur (Zone-B) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE_RAJIB BISWAS,Junior Engineer-I | ORD/000847/2021-2022 | 103/BD-I | 01/02/2022 | 22/11/2025 | DOBAY CONSTRUCTION | 261.58 | 162.27 | 62.03 | 92
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | Retrofitting | Formal Work Order for laying of balance portion and relaying of damage portion in different dia on different nodes of UPVC and DI (K-7) pipe line under Gopinathpur (Zone-B) Surface based water supply scheme under uncovered arsenic areas of Beldanga-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-I | ORD/000844/2021-2022 | 100/BD-I | 01/02/2022 | 02/05/2022 | C.X.CONSTRUCTION & CO. | 119.44 | 0 | 0 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | Retrofitting | Trial run of distribution system pipeline(CI/DI/UPVC/HDPE) and allied works at Gopinathpur Zone of Surface based water supply (under Central Sector Part-II) Scheme under JJM for uncovered arsenic affected area of Beldanga-I under Berhampore Division-I, PHE Dte Period for 3 Months. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000426/2023-2024 | 284/BD-I | 20/02/2024 | 20/05/2024 | JAMIRUL CONSTRUCTION | 6.67 | 6.6 | 98.91 | 100
Total | [13 empty] | 422.35 | 168.87 | 39.98