## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dangapara,Bati & Char Ramipur (Village code 314887,314888 & 314889) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000260/2021-2022 | 1048/BD-I | 21/06/2021 | 20/08/2021 | BOSE & CO | 98.62 | 77.92 | 79.01 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tentulia & Char Chatra (Village code 314873 & 314874) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000294/2021-2022 | 1180/BD-I | 16/07/2021 | 12/01/2022 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 114.26 | 98.18 | 85.93 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasenpur (Village code 314886) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000295/2021-2022 | 1181/BD-I | 16/07/2021 | 12/01/2022 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 117.76 | 105.56 | 89.64 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Neoai Khamarpara, Purba Gobindapur & Rampur (Village code 314876,314883 & 314884) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000259/2021-2022 | 1047/BD-I | 21/06/2021 | 20/08/2021 | A ONE CONSTRUCTION | 83.87 | 71.41 | 85.14 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharmmapur (Village code 314875) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000276/2021-2022 | 1169/BD-I | 15/07/2021 | 13/10/2021 | SHYAMAL KUMAR SAHA | 84.96 | 72.88 | 85.78 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanksa & Hulaspur (Village code 314882 & 314885) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000221/2021-2022 | 1019/BD-I | 21/06/2021 | 20/08/2021 | RAJ KUMAR MONDAL | 78.07 | 65.04 | 83.31 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nesta & Kumirdaha (Village code 314871 & 314872) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000220/2021-2022 | 1018/BD-I | 21/06/2021 | 20/08/2021 | MODERN CONSTRUCTION | 80.88 | 76.68 | 94.81 | 85
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Rampur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000852/2021-2022 | 133/BD-I | 08/02/2022 | 09/05/2022 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 79.8 | 77.93 | 97.65 | 100
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Laying of CI/DI pipeline and sluice valve with chamber at different places under Rampur Zone-C,central sector part-I under JJM under Berhampore Division-I ,P.H.E Dte. In the district of Murshidabad. | Assistant Engineer-I |  | ORD/000258/2024-2025 | 2271/BD-I | 16/12/2024 | 15/01/2025 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 5.02 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 31.12.2025 | Assistant Engineer-I | JE | ORD/000267/2024-2025 | 2328/BD-I | 27/12/2024 | 27/12/2025 | TARUN KUMAR BHATTACHARYA | 1.81 | 0.8 | 43.82 | 0
Total | [13 empty] | 877.51 | 654.06 | 74.54