## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | SM/08899 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of NADAIPUR (Village code 314205) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer,Assistant Engineer-I | JE,Junior Engineer-I | ORD/000249/2020-2021 | 921/BD-I | 11/12/2020 | 31/12/2025 | H.I ENTERPRISE | 95.04 | 18.68 | 19.66 | 59
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | SM/08899 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 315210), Upar Fatepur (Village Code 314212) & Bajupur Madhupur (Village Code 314235) under Bajupur Madhupur Ground Water Supply Scheme for Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000299/2020-2021 | 994/BD-I | 17/12/2020 | 15/06/2021 | BIJOY CHOWDHURY | 253.85 | 176.93 | 69.7 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | SM/08899 | Retrofitting | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 12/02/2022 | BIJOY CHOWDHURY | 13.36 | 10.9 | 81.53 | 1
Total | [13 empty] | 362.26 | 206.51 | 57.01